## Sheet1
MODULES: |  |  |  | TEAM-MEMBER | TASK HOURS | PERCENT-COMPLETED | REMARKS
1 | User Login & Validation | [6 empty] | MODEL | SERVICE/BUSINESS LOGIC/DATA
|  | MODEL | USERID VALIDATION WITH DB |  | 16 |  |  |  | SERVER SIDE VALIDATION
|  |  | DB COMMUNICATION-REST API? |  | 16 |  |  |  | REST API CALL
|  |  | LOGIN EVENT |  | 4 |  |  |  | WEB-SERVICE CALL
|  |  | MY FCA REWARDS DASHBOARD CLICK EVENT |  | 4
|  | CONTROLLER | HIDE/SHOW/DATA-BINDING |  | 4 |  |  | CONTROLLER | HIDE/SHOW/DATA-BINDING
|  |  | PAGE REDIRECT |  | 2
|  |  | PAGE RELOAD |  | 2
|  | VIEW | LOGIN PAGE/DEALER CONNECT |  | 4 |  |  | VIEW | HTML/CSS/BOOTSTRAP
DEALER CONNECT HOME-MY FCA DASHBOARD
[8 empty] | TESTING | UNIT TESTING
|  | TESTING | UNIT TESTING |  | 20 |  |  |  | (KARMA-JASMINE)
(KARMA-JASMINE)
INTEGRATION
|  | INTEGRATION | INTEGRATION OF ALL COMPONENTS IN A SINGLE MODULE |  | 8
|  |  |  | TOTAL | 80 |  |  | SQL SERVER-2016
2 | HEADER | [6 empty] | DB ACCESS
|  | MODEL | LOAD ALL THE STATIC CONTENTS |  | 8
|  |  | CLICK EVENTS IN FCA |  | 4
|  |  | MY-PROFILE-LOGOUT EVENT |  | 4
|  |  | CONTACT US EVENT |  | 4
|  | CONTROLLER | REDIRECTING THE VIEWS ACCORDING TO THE EVENTS |  | 8
|  | VIEW | STATIC HEADER CONTENTS VIEW |  | 4
|  |  | FCA CRYSLER AUTOMOBILES VIEW |  | 4
|  |  | CONTACT US VIEW |  | 2
|  | TESTING | UNIT TESTING |  | 16
(KARMA-JASMINE)
|  | INTEGRATION | INTEGRATION OF ALL COMPONENTS IN A SINGLE MODULE |  | 8
|  |  |  | TOTAL | 62
3 | WELCOME
|  | MODEL | FETCHING USER-RELATED DATA |  | 16
(Name, Designation, Picture, dropdown?)
|  | CONTROLLER | LOAD WELCOME VIEW |  | 8
|  | VIEW | WELCOME VIEW |  | 4
|  | TESTING | UNIT TESTING |  | 16
(KARMA-JASMINE)
|  | INTEGRATION | INTEGRATION OF ALL COMPONENTS IN A SINGLE MODULE |  | 8
|  |  |  | TOTAL | 52
4 | MENU-BAR/NAV-BAR
|  | MODEL | HIDING AND SHOWING THE MENU-BAR ACC. TO USERS |  | 16
|  |  | CONTENT-LOADING FOR MENUS |  | 8
|  |  | IMAGES-LOADING ACC. TO USERS |  | 8
|  | CONTROLLER | REDIRECT THE PAGES ACCORDING TO USER CLICK EVENT |  | 8
|  | VIEW | MENU BAR VIEW AND CAROUSEL IMAGE VIEW |  | 16
|  | TESTING | UNIT TESTING |  | 16
(KARMA-JASMINE)
|  | INTEGRATION | INTEGRATION OF ALL COMPONENTS IN A SINGLE MODULE |  | 8
|  |  |  | TOTAL | 80
5 | BODY/CONTENT-LOADING
|  | MODEL | TILES LOADING ACCORDING TO THE USERS |  | 16
|  |  | FETCHING DATA FROM DATABASE AND DISPLAY IN THE VIEW |  | 16
|  | CONTROLLER | REDIRECT THE PAGES ACCORDING TO USERS CLICK EVENT |  | 16
|  | VIEW | TILES VIEW (tiles size is dynamic according to the content) |  | 8
|  |  | VISIT PROGRAM SITE VIEWs |  | 2
|  |  | VISIT MOPAR.Dealer.com |  | 2
|  |  | VISIT Learning Center Site VIEW |  | 2
|  |  | LEARN MORE….(FOR-DEALER) |  | 2
|  |  | FCA REWARDS REDEMPTION(SHOP NOW VIEW) |  | 2
|  | TESTING | UNIT TESTING |  | 24
(KARMA-JASMINE)
|  | INTEGRATION | INTEGRATION OF ALL COMPONENTS IN A SINGLE MODULE |  | 16
|  |  |  | TOTAL | 106
6 | FOOTER
|  | MODEL | LIVE CHAT PLUGIN INTEGRATION |  | 8
|  |  | QUESTION/CALL PLUGIN INTEGRATION |  | 8
|  | CONTROLLER | REDIRECT TO LIVE-CHAT BOX VIEW ACC. TO USERS CLICK EVENT |  | 4
|  |  | REDIRECT TO CALL VIEW ACC. TO USERS CLICK EVENT |  | 4
|  | VIEW | LIVE CHAT AND CALL PLUGIN VIEW |  | 4
|  |  | LIVE CHAT BOX VIEW |  | 4
|  |  | CALL QUESTIONS VIEW |  | 4
|  | TESTING | UNIT TESTING |  | 16
(KARMA-JASMINE)
|  | INTEGRATION | INTEGRATION OF ALL COMPONENTS IN A SINGLE MODULE |  | 8
|  |  |  | TOTAL | 60
PROJECT INTEGRATION
| INTEGRATION OF ALL THE MODULES |  |  |  | 16
| INTEGRATION TESTING |  |  |  | 8
|  |  |  | TOTAL | 24
| FULLY-FUNCTIONAL APPLICATION |  |  | TOTAL | 464